MULTILATERAL INVESTMENT FUND      |      PROJECT ABSTRACT

PROJECT NAME: Competitive Improvement and business consolidation of small producers for the substitution of illegal drug production in Colombia

PROJECT NUMBER: CO-M1089

PROJECT TEAM: Alejandro Pardo (MIF/AMC), Alejandro Escobar (MIF/ AMC), Martha Lucia Muñoz (MIF/CCO), Carlos Guiza (MIF/AMC), Clarissa Rossi (MIF/AMC), Aránzazu Ruiz (MIF/AMC), Héctor Castello (MIF/CAR), Carla Bueso (MIF/DEU), and Laila Choe (MIF/KSC).

- PROJECT SUMMARY

The production of illegal drugs has become a destabilizing force for social and economic development in LAC. In Colombia, governmental programs supported by the US government to eradicate illegal drugs’ production have been particularly active in the last decade, with a focus on enforcement and subsidies, and a dependency on fiscal endowments.  Since 2008, the MIF in partnership with the United Nations Agency on Drugs and Crime (UNODC) tested the effectiveness of a market-driven incentive for the substitution of illegal crops in Colombia. The pilot permitted to develop and test a method based on developing direct links with high-value markets that allowed an initial sample of 56 small producers’ organizations to obtain significantly higher returns for legal crops as opposed to illegal crops. It employed multi-pronged marketing strategy composed of (i) high-quality product certification and the exploitation of the Products for Peace branding, (ii) shifting of production to premium-price products (premium cocoa and coffee, gourmet chocolate, palm-hearts preserves, and multi-flower honey). (iii) The development of retailing agreements with leading Colombian retailers such as Carrefour and Almacenes Éxito, and (iv) agreements with large export clients like Illi Caffé and Mori.  An impact evaluation conducted by IDB-OVE showed economically significant positive results for the treated population. The study is also strongly suggestive of an increasing impact among the smaller producers of the intervention, effectively providing a positive expectation that the project can be successfully expanded toward lower-income producers. This finding and the evaluation results are more broadly being used in the design of this scale-up intervention. A recent assessment potential on potential markets reveals emerging market opportunities both by diversifying products and by significantly expanding sales in identified trade channels. The opportunity to scale up is also being supported by GOC which is launching an inter-ministerial initiative for a more integrated policy planning and public management in drug-producing regions. This step is both an enabling condition for successful scaling up, and a clear signal of GOC’s commitment to the project’s model. Despite these opportunities for scaling-up the project, the problem this project aims to address is that the vast majority of small producers in drug-producing regions are not endowed with sufficient business capacities and an enabling business climate to respond to market-driven incentives in order to produce a significant regional productive shift towards legal crops. Based on MIF experience in scale-up projects, this intervention will develop the necessary knowledge and governance conditions to refine and bring to scale a method to complement substitution of illegal crops policies by providing market-driven incentives in  16 identified regions in Colombia. Bringing the model to scale implies a number of adaptations from the previous model including reinforcing inter-institutional collaboration, expanding organizational capacity thorough outsourcing of TA services, and moving towards a multilayered intervention model according to the organizations’ degrees of preparedness.

- PROJECT CONTRIBUTION TO THE ACCESS FRAMEWORK

The project contributes to the achievement of MIF’s mission: “support private sector-led development benefitting the poor - their businesses, their farms, and their households. The purpose is to give low-income populations the tools to boost their incomes: access to markets and the skills to compete”. The project is part of two agendas under the Access to Markets and Capabilities area: “Models for Local Economic Development (LED)”, and “Linking Small Producers to High-Value Markets” (HVM). The results of the project are focused on increasing small producers’ income at their household, business, and regional levels, which are aligned with the key expected results of the agendas. In terms of knowledge, the project will test hypothesis on the necessary conditions to scale market-driven incentives among different strata of producer size and capabilities in a setting characterized by the presence of strong incentives for illegal production. These results can be used to disseminate knowledge on how to bring long term programs that complement illegal-drug production eradication policies to scale at the regional level.

- INFORMATION

| COUNTRY: | Colombia | MIF FUNDING: TECHNICAL COOPERATION: | US$2,000,000 | 23% |
| --- | --- | --- | --- | --- |
| LOCATION: | 16 Colombian States | COUNTERPART: UNODC Occidental Petroleum (OXY) Pacific Rubiales Agricultural Financial Fund (FINAGRO) GOC-DPS | US$6,700,000 | 76% |
| EXECUTING AGENCY: | United Nations Agency on Drugs and Crime (UNODC) | COFINANCING (IF AVAILABLE): |  |  |
| ACCESS AREA: | AMC | TOTAL PROJECT: | US$8,700,000 | 100% |
| AGENDA: | LED HVM | NUMBER OF DIRECT BENEFICIARIES: | 10,000 small producers and their families - corresponding to 150 small producer organizations |  |
| COMPLEMENTARY BANK OPERATIONS (IF ANY): |  | NUMBER OF INDIRECT BENEFICIARIES: |  |  |
|  |  | QED SCORE: | 9.67 |  |

- PROBLEM DIAGNOSIS

The problem this project expects to address is that the vast majority of small producers in the 16 identified regions are not endowed with sufficient business capacities and an enabling business climate to respond to market-driven incentives in order to produce significant regional productive shift towards legal crops. Currently, there is a census of 542 small producers’ organizations in regions covered by governments’ programs to eradicate illegal drug production which did not benefit from the pilot phase. According to data from UNODC, the total area of hectares of coca cropped in the country is still 61,811 hectares.

Cause I. Public sector strategies in regions affected by illegal drug production features limited sustainability of benefits from government enforcement measures or welfare programs, shortcomings in terms of adequacy to the business needs of small producers and private investors, and business climate deficiencies (i.e.: legal uncertainty, trade channel oligopolies, and transportation security).

Cause II. The vast majority of small producers in these regions have diverse business shortcomings to access high-value markets and their production is limited to local small-scale markets and self-consumption. Product development and differentiation, quality management, and trade links necessary to access high-value markets is generally limited.

Cause III. Small independent producers are isolated and disconnected with a variety of larger market players.  Small farmer organizations are still weak and unable to improve purchasing and negotiation power. Individual initiatives to position products in the market tend to fail as economies of scale have not been reached.

Classify the problem in one or more of the following categories that most apply:7

Market failure         			 	 Skill deficit

Institutional weakness        			 Collective action problem

Policy weakness/failure    			 Lack of appropriate technology

OTHER (Explain as needed) ___________

The direct beneficiaries for this project are: at least 150 organizations comprising 10,000 small producers in 16 regions in Colombia affected by illegal drug production and with a high incidence of poverty. The 10,000 small producers who use to grow illegal crops are now committed to collaborate with the GOC and shift to legal productions. Most of the selected producers show high incidence of poverty and shows diverse degrees of preparedness to access high-value markets. About 12,000 additional small producers in the regions are expected to benefit from the externalities of the project, demonstration effects and the consolidation of legal regional markets.

- PROJECT DESCRIPTION

The project’s objective is to upgrade (refine and bring up to scale) a method to complement government policies for the substitution of illegal crops by providing inclusive market-driven incentives to small producers in 16 identified regions in Colombia.

The pilot project supported by the MIF permitted to develop and test a previous method based on developing direct links with high-value markets that permitted an initial sample of 56 small producers’ organizations (3,000 families) to obtain significantly higher returns for legal crops as opposed to illegal crops. It employed multi-pronged marketing strategy composed of (i) high-quality product certification and the exploitation of the Products for Peace branding, (ii) shifting of production to premium-price products (premium cocoa and coffee, gourmet chocolate, palm-hearts preserves, and multi-flower honey). (iii) the development of retailing agreements with leading Colombian retailers such as Carrefour and Almacenes Éxito, and (iv) agreements with large export clients like Illi Caffé and Mori.Bringing the intervention to scale implies a number of adaptations of the intervention model, like: (i) reinforcing inter-institutional collaboration both private-private and public-private at the regional level; (ii) expanding organizational capacity thorough outsourcing of technical assistance services and strategic alliances with key players in each territory, (iii) moving towards a multilayered intervention model that will vary its types of interventions according to the diverse organizations’ degrees of preparedness; and (iv) emphasizing management for results and impact evaluation as a key component of up-scale strategies.

The intervention will consolidate the previous pilot experience targeted to a selected sample of organizations into an institutionalized inclusive process for upgrading small-producer organizations to identified high-value markets. In a nutshell, it contemplates: (i) an entry level (that will allow to include a large number of organizations according to a diagnosis), (ii) a consolidation level (that will upgrade organizations to incorporate them to high-value markets), (iii) a market-ready level (that strength the position of small producers to identified high-value markets) and (iv) an exit-level (that will permit graduation for producers that can sustainably continue their business). Eligibility criteria and thresholds for different interventions have been defined based on the selection criteria validation findings on the impact evaluation carried out for the pilot project. Based on this study, eligibility criteria can be modified so as to admit smaller and less capable producers, while still maintaining program effectiveness. The financial viability of the project is based on a business model based on fee-for-service related to brand-use, product development, quality certification, logistics, and trade. Pricing will be determined according to the above-mentioned thresholds and range from a 40% over costs for organizations at entry level to 120 over costs for graduated organizations.

The project has the following components:

Component I. Governance. The objective of this component is to systematically develop inter-institutional arrangements between private and public actors in the territory that proved successful during the pilot phase, despite the fact that they were not planned in the pilot. In addition, the component will permit complement GOC integrated planning and policies in drug-producing regions (Planes de Consolidación) with private sector driven processes.  Plans will be executed by a committee that includes the participation of public institutions, NGOs, research institutes, corporate organizations and other stakeholders involved in decision-making for business development.

Component II. Development of businesses for high-value markets. The objective of this component is to transfer the technical assistance method developed during the first phase. That assistance focused on (i) strengthening producer’ organizations and small producers’ readiness to engage in high-value markets (including new product development). (ii) Promoting quality management and certification, (iii) marketing strategy improvements, (iv) logistic management, (v) access to rural finance (FINAGRO), and (vi) good environmental and organic certification and food-handling practices. Based on good diagnosing practices developed during the pilot phase, this component will adapt and test different interventions in line with the diverse organizations’ preparedness for identified high-value markets (premium cocoa and coffee, gourmet chocolate, palm-hearts preserves, and multi-flower honey, among others).

Component III. Associative and Collective Goods. The objective of this component is to strengthen the producers’ downstream and upstream associativity, as this can be a key driver for the inclusion of new players in high-value markets. Alliances will permit producers to obtain preferential prices on supplies, fertilizers, marketing and transportation of products, to develop and umbrella proprietary brand, and to collectively negotiate commercialization agreements with key market players.

Component IV. Learned lessons and scale up. The objective of this component is to develop and transfer knowledge to provide incentives to small producers and to feed governmental and private strategies for the substitution of illegal drugs in Colombia. Building upon the EA knowledge development and communication strategies, the  methods tested will be assessed with rigor in order to produce communication materials to reach identified audiences, especially the Department of Social Prosperity and the Consolidation Plan that are in charge of the design and implementation of the country´s policy against illegal drugs, and private investors in these regions.

The knowledge goal of this project is to document the market driven incentive model for the substitution of illegal crops, refined and scaled-up by the project. To this end, a comprehensive case study -including results, key lessons and testimonials from the beneficiaries and stakeholders- will be produced and disseminated to the following audiences in order to achieve broad demonstration effect as well as to inform public policy: (i) Local governments of other regions affected by illegal drug production, (ii) Small producer organizations and other community based organizations in regions affected by illegal drug production, (iii) Government agencies/policy makers in charge of the design and implementation of the country’s policy against illegal drugs, and (iv) Potential buyers of the products, including major local retailers as well as international brands. The execution of this component will build on the significant expertise that UNODC possess in the area of knowledge management and strategic communications.

Explain MIF or other organizations’ experience and acquired expertise in similar projects. Include evidence of the effectiveness of the intervention based on experience in other settings or previous experience in the same setting.

MIF and UNODC have successfully executed the pilot project ATN/ME–10392-CO “Strengthening business and agro industrial capacity of alternative development producers”. The project was recently evaluated using quasi-experimental evaluation methods under OVE’s supervision. The evaluation found that the project was adequately targeted as most of the organizations treated by the program were located in areas of the country with high presence of coca leafs. The evaluation also found positive effects in terms of small businesses performance, product quality management, and organizational development: (i) In terms of small-business performance, the evaluation found that the project has positive results in terms of increasing of sales of different crops -29% higher than control organizations, which corresponds to a difference of more than $140 million Colombian Pesos and in terms of increasing productive capacity area -16% higher than that of the control group, which corresponds to a difference of 57 to 100 hectares; (ii) In terms of products’ quality management, the evaluation found that the program also had a positive effect on the product's quality index (defined as the number of quality seals or certifications over the total number of products of each productive line). The participating organizations had a quality index that was almost 200% higher than the control organizations; (iii) In terms of organizational performance, the evaluation found the participating organizations had subscribed more strategic agreements with public and private institutions than the control organizations and this was a key aspect of project success. This result is mainly driven by an increase in the number of agreements with public agricultural and environmental certification institutions as well as with the private sector (including financial institutions, private firms and other organizations of producers). In addition, the evaluation found that the probability that the participating organizations had trade finance agreements to support trading activities for its members was 17% higher relative to the control organizations. Although the treatments were tailored to the needs and scale of individual producers, the evaluation also produced findings suggestive of large results among smaller and less developed producers, which opens up an opportunity for scaling-up operations in these markets.

The project is also based on available evaluations of USAID assistance experience of Plan Colombia, and other programs in different settings and on UNODC programs to support eradication of illegal drug production worldwide.

Finally, this project is also based on MIF experience and lessons learned of scaling up pilot projects in broader scenarios; as in the cases of IYF youth training projects in Brazil, Argentina and Colombia. The proposed intervention is also being designed bearing in mind scale-up experiences of LED initiatives in Argentina, Peru and Brazil.

Outline lessons learned and/or best practices and how the project will incorporate these lessons in the project design.

The impact evaluation and MIF experience in other settings identified some key lessons learned for project success effectiveness: (i) elaborating in-depth diagnostic studies to identify the needs of the participant organizations; (ii) providing a heterogeneous “treatment” according to the needs of each organization that oriented a multilayered model; (iii) strengthening public-private relationships and formal agreements;  (iv) reaching smaller organizations through the effective role of an organized network (second level organization) for the delivery of services and technical assistance through second level organizations proved to be effective in reaching effectively smaller organizations, (v) reaching higher returns for relatively smaller organizations; (vi) planning scale-up processes by reinforcing high-impact drivers of pilot phases, adapting the model for a broader scope, reorganizing the delivery of services including outsourcing options, developing broader partnerships, and reinforcing management for results and impact evaluation.

- MIF ADDITIONALITY

MIF Non-Financial Additionality: Discuss briefly what the MIF brings to the project in terms of non-financial contribution, which may include reputation, image, credibility, technical expertise, brand recognition, leverage potential, partner networks, skills complementing those of the executing agency, or synergies with other existing operations.

MIF’s non-financial additionality is given both by addressing a market failure and by providing technical value-added: (i) the project brings to market a scaled solution in a distorted market caused by the existence of an illegal alternative market; (ii) the project relies on MIF experience in integrating private and public initiatives under efficient governance frameworks; (iii) the project is based on MIF focus and experience in accompanying scale-up processes.

MIF Financial Additionality: Explain why MIF financial participation is critical for developing the project (there is little or no alternative funding).

MIF financial additionality is provided by MIF leverage that is being instrumental to gather the financial resources necessary for bringing to scale the pilot project, including the key international (UNODC), national governmental (DPS-GOC), public-private (FINAGRO) and private actors (Pacific Rubiales-OXY). This gap in the government’s illegal crops substitution policy makes the financial participation of the MIF fundamental to leverage public and private funds.

- PROJECT RESULTS

Provide preliminary estimates of quantitative and/or qualitative metrics that will be used to track and measure project results by sex and/or by beneficiary groups identified in the problem diagnosis (where relevant).

Project results

a. At least 10,000 small producers’ applying better financial management, quality and marketing practices

b. 3 additional international and 2 national markets opened

c. 4 new product lines commercialized

d. At least 30 – 50 small producers’ organizations subscribed contracts to improve access to finance (i.e. credit from financial institutions), to improve access to markets (i.e. promote their products in high value markets) and access to services (i.e. quality certifications, government sponsored services)

e. At least one public-private inter-institutional agreements signed in each region

f. At least 8 small producers’ organizations graduated from the project

Adoption and scaling: Mention if some partners and/or other institutions have been already identified or manifested their interest in scaling up the results of the operation.

The project is being sponsored by a consortium of partners that have already manifested their interest in scaling up the results of the operation: (i) the Consolidation Unit and the Department of Social Prosperity (DPS) of the GOC that are in charge of coordinated public policies in regions affected by illegal drug production, (ii) Occidental Petroleum Corporation (OXY) and Pacific Rubiales Corporation that are heavily investing and developing CSR programs for productive development in affected regions, (iii) The Agriculture Financial Fund (FINAGRO) that will use the program to expand its lending to uncovered areas with lower market risk; (iv) Swisscontact, that will technically reinforce UNODC team for a broader scope and will support the development of a service provision network as a key component of scale-up strategies. UNODC is the leading UN agency in this topic and is eventually planning to partner with the MIF for the expansion of this model to other identified countries like Peru and Ecuador.

- PROJECT IMPACT

Provide quantitative and/or qualitative metrics of the desired impact in terms of social, economic, quality of life and environmental benefits for direct and indirect beneficiaries by sex and/or by the beneficiary groups (e.g. changes in income, changes in income control, poverty reduction, consumption, jobs, sales and revenues, exports, business created, profits, health, nutrition, education, etc.). In addition provide metrics for impact on climate change where relevant

Small business performance and income generation for small producers:

- 30% average sale increase for each product (cocoa, palm, honey, etc.) at the organization level in national and international markets.

- 20% household income increase for small producers participating in the project

- 20% average increase in employment in participating small farms

Regional Impact:

- 45% increase in land hectares dedicated to legal crop production by treated small producers

* These targets are based on preliminary calculations of the pilot phase’s impacts.

- BASELINE DATA, MONITORING MECHANISMS AND EVALUATIONS

Indicate how baseline data on the relevant economic and social indicators for the beneficiary population will be established (include poverty, income, consumption, control over income, jobs, sales and revenues, exports, other business characteristics, health, nutrition, education, , location and carbon emissions metrics, as relevant). All data should be sex disaggregated.

The United Nations Agency on Drugs and Crime (UNODC) and DPS have already collected baseline  information about the census of organizations participating in the different illegal crop substitution programs, including information at the organization level and aggregated data at the business level. This baseline data will be complemented with a strong linkage with governmental data (RED UNIDOS) at the individual level (small producers’ data) including poverty level, household income, and living conditions, data can also be disaggregated by gender.

Describe the planned monitoring mechanisms that will be used to collect and track the data in order to measure project results and impact.

This project will use the monitoring system developed by the UNODC during the previous phase of the project.

Describe how the project will be evaluated. Mention the main evaluation questions. Indicate if the project will have an impact evaluation. Indicate why the project is suited to an impact evaluation (e.g. strategic value, knowledge gap, potential for expansion, statistical characteristics, etc.)

The project will carry out the first impact evaluation on scale-up theory to verify the effectiveness of a different combination of components and to evaluate model adaptation and dilution of benefits when replicating the method to other organizations which are more heterogeneous. Empirical data on the effectiveness of scaled up projects is very limited. Thus generating evidence based data in this topic might be important policy implications. The impact evaluation will focus on measuring the performance of different type of organizations: graduating, consolidating and entering the method, their market success in terms of sales, the project´s impact on poverty, and their contribution to reduce illegal crop reduction. The evaluation will also allow the team to perform cost-effectiveness analysis of the program as a whole.

- EXECUTING AGENCY

Provide a brief description of the executing agency, discussing its strengths and potential weaknesses for implementing the proposed project. Mention the institution’s previous experience with multilateral development banks and MIF. Include key findings regarding institutional integrity from the on line application.

The United Nations agency on drugs and crime (UNODC) will be the executing agency for this project. UNODC has worked in Colombia over the last 20 years, on illegal crop substitution and alternative development projects. Together with the MIF, it executed the project ATN/ME–10392-CO “Strengthening business and agro industrial capacity of alternative development producers” that became a successful reference for the scale up of the present project. The project is based on a strategic alliance with Swisscontact, which will reinforce UNODC capacity for the provision of technical services for a broader audience particularly for the international commercialization of cocoa.

Explain how the project fits the institution’s core business and whether the project is aligned with the institution’s priorities and overall mission.

UNODC’s mission is to support governments to develop alternative ways to find sustainable economic practices wherever there are illicit crops and organized crime. The project is directly related to this main line of work.

Mention if other partners will be involved in the project and their roles.

UNODC has identified as its main funding partners: the Department for Social Prosperity DPS) that coordinates and executes development projects that address the poorest of the poor, The Ministry of Agriculture and Rural Development (MADR), whose main purpose is to develop policies that support rural development, the financial fund for the agriculture sector (FINAGRO), the government´s consolidation unit and the vice presidency’s technical secretariat for children recruitment prevention, besides the private partners mentioned above, and Swisscontact. This partnerships warrant a more integral public-private approach and the availability of technical and financial inputs necessary for engaging in the projects’ broader scope.

- PROJECT RISKS

Identify potential risks that may impede achievement of the project’s development objectives.

Market’s Risks. i) project may not maintain the interest of private enterprises in generating investment and commercial partnerships with producer groups; ii) the capacity of the “fair-trade demand” segment to purchase the products developed may be affected; iii) export performance may be affected by exchange rates and variations in the markets demands; and iv) although the program data suggest market scaling is sustainable among smaller producers, it is possible that smaller producers will not see sufficient benefits in order to make the program sustainable among all producer strata targeted.

Social Risks. i) The security in regions affected by illegal drug production is an important risk that should be carefully monitored; ii) the small producers might fail to generate a joint effort to create the necessary synergies for participating in the market.

Regional Risk:  i) illegal traffickers may delocalize production to other regions in Colombia or other countries.

- ENVIRONMENTAL AND SOCIAL ASPECTS

Describe if there are any positive or negative environmental or social spillover effects. Highlight if the project includes any important aspects regarding social inclusion or indigenous groups. If there is the risk of negative spillover effects mention how the project is planning to mitigate it.

The model implements the adoption of Good Agricultural Practices (GAP) as a market competitive advantage and assures the families’ commitment to the recuperation and conservation of ecosystems affected by illicit crop expansion.

- COUNTRY OFFICE COMMENTS

Any other comments pertaining to any of the previous sections, the project’s viability, executing agency capacity or other issues from the Country Office Specialists should be included in this section.

The method developed by the UNODC has shown an important positive impact. Its improvement and scale-up will definitely contribute to the policies the government has developed over the past ten years.

Annual Report on Drug Production in Latin America (United Nations Office for Drugs and Crime - UNODC, July 2012)

GOH’s programs to eradicate drug production have included: military/police oversight, aerial spraying programs and/or manual eradication, and more recently directs stipends and/or conditional cash transfers linked crops shift.

ATN/ME-10392-CO – Project completion Report - 2011

Creating New Opportunities for Rural Producers: Impact Evaluation of a Pilot Program in Colombia: Sandra Rozo (UCLA University)/ OVE (OVE, 2012).

Plan Nacional de Consolidación (Departamento de Prosperidad Social- Colombia 2012)

Annual Report on Drug Production in Latin America (United Nations Office for Drugs and Crime - UNODC, July 2011)

The regions are: Cauca, Antioquia, Bolívar, Chocó, Magdalena, Santander, Norte de Santander, Putumayo, Huila, Guaviare, Caquetá, Arauca, Córdoba, Sucre, Nariño, y Tolima. The regions were selected by the Colombian Government and UNODC according to criteria regarding high incidence of illegal drug production.

United Nations agency on Drugs and Crime (UNODC). Baseline report on Strengthening business and agro industrial capacity of alternative development producers. 2008

ATN/ME-10392-CO – Project completion Report - 2011

United States Government Accountability Office (2010). Retrieved from: http://www.gao.gov/products/GAO-10-921T”